## Sheet1
Sprint 1
| September 18 - 25 |  | Build and Deploy a demo Flask application to heroku
Sprint | week | # | Task | Assignee | Status | Hours | Dependency | Status
1 | September 18 - 25 | 1 | Design the database models | Divya, Krishna | In Progress | 1
1 | September 18 - 25 | 2 | Implement Database models/tables in PostgreSQL | Krishna | Finished | 1 | 1 | Finished
1 | September 18 - 25 | 3 | Learn about Flask and check tutorials | Divya | Finished | 1
1 | September 18 - 25 | 4 | Set up a demo flask application on localhost | Divya | Finished | 0.5 | 3 | Finished
1 | September 18 - 25 | 5 | Design API following API Design Principles | Krishna | Finished | 0.5
1 | September 18 - 25 | 6 | Create APIs to handle basic requests and API routes in Flask | Divya | Finished | 0.5 | 5 | Finished
1 | September 18 - 25 | 7 | Set up a Heroku Account | Divya | Finished | 0.5
1 | September 18 - 25 | 8 | Deploy to Heroku | Krishna | Finished | 0.5 | 7,8 | Finished
1 | September 18 - 25 | 9 | Plan next Sprint | Divya, Krishna | Finished | 0.5 | 9 | In Progress
[5 empty] | Total Hours: | 6
|  |  |  | TeamLead: | Krishna
|  |  |  | Scrum master: | Divya
Scrum Meetings:
Every Thusday and Monday from 11:00 AM to 11:20 AM

## Sheet2
Sprint 2
| Sept 26 - oct 2 |  | Deploy Basic APIs with Postgres and Flask application to heroku
Sprint | week | # | Task | Assignee | Status | Hours | Dependency | Status
2 | Sept 26 - oct 2 | 1 | Create PostgreSQL functions to be called from Flask | Krishna | In Progress
2 | Sept 26 - oct 2 | 2
2 | Sept 26 - oct 2 | 3
2 | Sept 26 - oct 2 | 4
2 | Sept 26 - oct 2 | 5
2 | Sept 26 - oct 2 | 6
2 | Sept 26 - oct 2 | 7
2 | Sept 26 - oct 2 | 8
2 | Sept 26 - oct 2 | 9
2 | Sept 26 - oct 2 | 10
|  |  |  | TeamLead: | Krishna
|  |  |  | Scrum master: | Divya
Scrum Meetings:
Every Thusday and Monday from 11:00 AM to 11:20 AM